## Slide 1: CWOP Angsi Besar Infill 5 CT Job Scope

## Slide 2: Table of Content:
1. Introduction & Well Overview
    Objective & Well Background
    Well Schematic
2. Job Execution
    Operation Summary
    Lifting Plan
    Well Stack Up
    CT P&ID
    VOS Flowback Setup
    CT Operation Timing
    Fluid Consumption Summary
    Decision Tree CT Run #1 (Cleanout to 10m below I-105 fracsleeve @ 2,155m MDDF) - Contingency
    Decision Tree CT Run #2 (Cleanout to 10m below I-100 fracsleeve @ 2,046m MDDF) - Contingency
    Decision Tree CT Run #3 Contingency CT Milling until Float Collar @ 2,640m MDDF
    RCP Settling Test Result
3. Equipment Readiness

## Slide 3: Objective & Well Background
Objective
The objective of this job is:
To perform CT proppant cleanout inside tubing post fracturing until Float Collar at 2,640 m MDDF.
To perform CT set Nipples Plug at target depth 2,547 m MDDF
Well Background
  Angsi Besar Infill 5 is a single monobore completion complete with frac sleeve which planned to drill expected on November 2023 with maximum deviation of 71 degree at 1,230 m MDDF.

## Slide 4: Angsi Besar A-09 : Well Diagram
1st Contingency Cleanout with JB @ I-105 Frac Sleeve
2nd Contingency Cleanout with JB @ I-100 Frac Sleeve
3rd Milling of Limitless Dat and Cleanout til Float Collar
4th Post Milling Cleanout and Drift til Float Collar
Set Plug below I-122 Frac Sleeve
 | Parameter Value
Field | Angsi Besar Infill 5
Max. Deviation (degrees) | 71 degree @ 1,230 m MDDF
Min. Restriction (inch) | @ 2,036 m, 2,145 m, 2,532 m MDDF 3.505” (Frac Sleeve)
Tubing Specification | 4-1/2” Production Tubing, 12.6# ppf, 13Cr
Type of Fluid & Density | 12.8 ppg (Gel & RCP)
Top of Fluid | N/A (Assuming well full of Gel)
Current Well Status | N/A
Depth of zone, pressure & temperature | I-100: 2,031.3 m – 2,040.8 m MDDF (1,805 psi, 184 deg F) I-105: 2,139.9 m – 2,149.7 m MDDF (1,813 psi, 186 deg F) I-122: 2,527.8 m – 2,536.4 m MDDF (2,064 psi, 197 deg F)
Porosity | I-100: 22% I-105: 23% I-122: 21%
Permeability | I-100: 88 mD I-105: 96 mD I-122: 66 mD
Fracture Pressure | 5,014 psi

## Slide 5: Operation Summary

## Slide 6: Coiled Tubing Equipment Layout

## Slide 7: Coiled Tubing Equipment List
NO | ITEM |  |  |  |  | REMARKS
 |  | LENGTH (ft) | WIDTH (ft) | HEIGHT (ft) | (mT) | 
1 | 10ft Tool Container | 2.99 | 2.44 | 2.59 | 10 | 
2 | BHA Container | 4.8 | 1.2 | 0.8 | 10 | 
3 | Zone 2 Generator Set | 2.5 | 1.5 | 2 | 5 | 
4 | Jacking Frame | 3.76 | 3.23 | 3.86 | 7 | 
5 | Power Stand | 3.99 | 2.59 | 3.73 | 30 | 
 | Coiled Tubing Drum #604463 |  |  |  |  | 
 | Spreader Bar |  |  |  |  | 
6 | Hydraulic Power Unit | 2.99 | 2.44 | 2.59 | 11.34 | 
7 | X-11 Control Cabin | 2.99 | 2.44 | 2.59 | 7 | 
9 | Injector Head Basket | 2.99 | 2.44 | 2.9 | 12.7 | Store at supply boat once unpacked
 | Injector Head (HR560) |  |  |  |  | 
 | Side Door Stripper |  |  |  |  | 
10 | 13ft Cargo Basket | 3.96 | 1.68 | 1.8 | 10 | Store at supply boat once unpacked
 | BOP Control Cart |  |  |  |  | 
 | Single BOP |  |  |  |  | 
11 | Open Top Basket | 2.99 | 2.44 | 2.76 | 12 | Store at supply boat once unpacked
 | Gooseneck |  |  |  |  | 
 | Combi BOP |  |  |  |  | 
12 | Iron Rack | 3.51 | 1.64 | 1.67 | 7 | Store at supply boat once unpacked
13 | OTT Basket (Hoses) | 2.99 | 2.45 | 1.39 | 12.5 | Store at supply boat once unpacked
14 | Nitrogen Converter | 4.8 | 2.2 | 2.59 | 13 | 
15 | Nitrogen Tank | 2.99 | 2.44 | 2.59 | 12 | 
16 | Nitrogen Tank | 2.99 | 2.44 | 2.59 | 12 | 
17 | Nitrogen Tank | 2.99 | 2.44 | 2.59 | 12 | 
18 | Nitrogen Tank | 2.99 | 2.44 | 2.59 | 12 | 
19 | OTT Basket (Cons Oils) | 3.6 | 1.2 | 1.3 | 10 | Store at supply boat once unpacked
20 | OTT Basket (JB & FL) | 3.6 | 1.2 | 1.3 | 10 | Store at supply boat once unpacked
21 | OTT Basket (Misc) | 2.99 | 2.44 | 1.22 | 7 | Store at supply boat once unpacked
22 | Chemical Basket | TBA | TBA | TBA | TBA | Store at supply boat once unpacked
23 | Nitrogen Tank | 2.99 | 2.44 | 2.59 | 12 | Store at supply boat until needed

## Slide 8: Coiled Tubing Equipment (During Lifting)

## Slide 9: Well Stackup
Injector Head HR560 c/w 100” Gooseneck
Side Door Stripper
4-1/16” Lubricator
4-1/16” Combi BOP
4-1/16” Flowcross
4-1/16” Single BOP (Pipe/Slip)
Crossover to Geowell

## Slide 10: Coiled Tubing PnID

## Slide 11: VOS Flowback Setup

## Slide 12: CT Operation Timing
Run# |  | BHA | Time
 |  |  | Hrs
1 | Cleanout until 10m below I-120 Frac Sleeve (2,516.0m MDDF) | 2-1/8” PowerCLEAN | 15.0
2 | Cleanout until 10m below I-105 Frac Sleeve (2208.6m MDDF) | 2-1/8” PowerCLEAN | 13.0
3 | Cleanout until 10m below I-100 Frac Sleeve (2101.1m MDDF) | 2-1/8” PowerCLEAN | 13.0
4 | Post Frac Clean Out until Float Collar (2,702m MDDF) | 2-1/8” PowerCLEAN | 33.0
5 | Milling Limitless Dart until Float Collar (2,702m MDDF) | 3-3/8” Bear Claw Mill with 2-7/8” Motor | 27.0
Initial Rig Up : 10 hours (inc. rig up well stack on TD, PT, make up tool)
Rig down with IH : 5 hours
Rig up if IH on TD : 4 hours (inc. make up tool & PT)
Rig down without IH : 3 hours
** Timing for Rig Up & Rig Down

## Slide 13: Fluid Consumption Summary
Run# |  | 9.2ppg Brine (gal) | Seawater (gal) | Gel Quantity (bbls) | N2 Quantity (scf)
1 | C | 205 | 1,500 | 45 | 4,000
2 | C | 205 | 1,500 | 45 | 3,500
3 | C | 205 | 1,500 | 45 | 3,500
4 | P | 205 | 5,000 | 1,40 | 8,000
5 | C | 205 | 3,500 | 380 | 7,500

## Slide 14: 2-1/8 and 2-7/8 Motor with 2inch Coil

## Slide 15: Decision Tree : 1st Contingency Cleanout Run

## Slide 16: Run 1 : BHA Configuration
2-7/8” External Dimple Connector
2-7/8” CS Dual Flapper Check Valve
2-7/8” CS Hydraulic Disconnect
2-7/8” CS Circulation Sub
2-7/8” Straight Bars
2-7/8” PowerClean Nozzle

## Slide 17: Run 1 : Cleanout until 2,155m MDDF (10m below I-105) – Simulation Results
Percentage of Total Fill removed | 100%
CT Max Internal Pressure | 5,290 psi
Top of max formation Pressure | 2,229 psi
90-99% Solids at surface | 384.1 mins
Total Job Time | 573.6 mins
Pump Rate | 3.0 bpm

## Slide 18: Decision Tree : 2nd Contingency Cleanout Run

## Slide 19: Run 2 : BHA Configuration
2-7/8” External Dimple Connector
2-7/8” CS Dual Flapper Check Valve
2-7/8” CS Hydraulic Disconnect
2-7/8” CS Circulation Sub
2-7/8” Straight Bars
PowerClean Nozzle

## Slide 20: Run 2 : Cleanout until 2,155m MDDF (10m below I-105) – Simulation Results
Percentage of Total Fill removed | 100%
CT Max Internal Pressure | 5,539 psi
Top of max formation Pressure | 1,914 psi
90-99% Solids at surface | 297.3 mins
Total Job Time | 618.4 mins
Pump Rate | 3.0 bpm

## Slide 21: Decision Tree : 3rd Milling Limitless Dart until 2,640m MDDF (Float Collat)

## Slide 22: Run 3 : BHA Configuration
2-7/8” External Dimple Connector
2-7/8” CS Dual Flapper Check Valve
2-7/8” CS Hydraulic Disconnect
2-7/8” CS Circulation Sub
2-7/8” BiCO Downhole Motor
3.375” BearCLAW Mill

## Slide 23: Run 3 : Milling until 2,640m MDDF shoe collar – Simulation Results
Percentage of Total Fill removed | 99.5%
CT Max Internal Pressure | 3,169 psi
Top of max formation Pressure | 2,212 psi
90-99% Solids at surface | 931.0 mins
Total Job Time | 1108.8 mins
Pump Rate | 3.0 bpm

## Slide 24: RCP Settling Test
Proppant Settling @ 77F = 0%
Proppant Settling @ 140F = 0%

## Slide 25: RCP Settling Test
Proppant Settling @ 197F = 0%
Conclusion :
At different temperature, there’s no affect on the interaction between resin coated proppant and J572 gel at different temperature. Thus, it is safe to proceed with using J572 gel for cleanout of the resin coated proppant.

## Slide 26: Equipment Readiness Update
Item | Equipment | Update
1 | CT Unit | Operating Package (completed by early of Nov)
2 | 2inch CT | 
3 | Pumping Unit and Treating Line | 
4 | PCE for 2inch | 
5 | BHA – Bear Claw Mill Bit | Fabrication done, await shipment ETA : End of October
Target Date
SIT : 15th Nov 2023
Inspection Date : 18th Nov 2023